## Sheet1
MONITORING SHEET PROJECT 2026 |  |  |  | 2026-03-15
UNIT | NO | NO | DESCRIPTION | OPERATIONAL BRIEF (PR) |  | 22 | DESIGN (HoD) |  |  |  | 11 | PROJECT CONTROL |  |  | 8 | PROJECT MANAGEMENT TEAM |  |  |  | 11 | 50% | HANDOVER | 4
|  |  |  | BRIEF | RECEIVED DATE | BUDGET/ CAPEX | START DESIGN DATE | DESIGN APPROVAL (+1 month) | duration : delay(-) / + | BRIEF | WORKING DRAWING (+3 weeks) | TENDER START | APS = SPK RELEASED (+3 weeks) | duration : delay(-) / + | CONTRACT AMOUNT | COMMENCE DATE | END CONTRACT | ACTUAL COMPLETION | deviation : delay(-) / + | CURRENT SITE PROGRESS | REMARKS | BAST -1 | BAST-2
SPH | 1 | 1 | SPH TENNIS COURT INDOOR | resurfacing (painting) 2 indoor court | 2026-01-05 | [7 empty] | 2026-01-21 |  | 345696200 | 2026-01-19 | 2026-02-21 | 2026-02-17 | +4 | maintenance period |  | 2026-02-17
|  | 2 | SPH TENNIS COURT 3 | Repair crack and resurfacing | 2026-02-24 | [10 empty] | 2026-02-25 | 2026-04-14 |  | 30 | 60% on schedule. Resume on 1 April
AJK |  | 3 | MONAS 1-4 & CORRIDOR : CARPET, PADDED WALL & PARTITION | Replacement (ripped & uneven) | 2026-02-12 | 1558900000 | 2026-03-01 | 2026-04-01 | 17 | ID = internal primatama/ dim carpet
| #REF! | 4 | SOAP DISPENSER : guestroom, public area toilet and fitness center room |  | awaiting PR | 101640000
|  | 5 | Mezanine ballroom curtain |  | awaiting PR | 500000000
AKB | #REF! | 6 | 2025 : CANOPY & FACADE NORTH LOBBY | Redirected | 2026-01-05 | 156510000 |  | 2025-02-26 |  | to review material board by consultant |  | 2025-09-22 | 2025-11-24 |  | 149850000 | 2025-12-04 | 2026-01-28 | postpone due to LMIIR permission
|  |  |  | after permission from LMIIR 26 Feb 2026 | [11 empty] | 2026-04-06 | 2026-05-06 |  | 52
| #REF! | 7 | GLASS FACADE SOUNDPROOFING 26 ROOMS | dec 2025 : unit has agreed to close the sound leakage from ceilling prior to facade modification & measure the DB afterwards | 2023 | 1300000000
| #REF! | 8 | Make Over Drop Off Area / Tile Replacement |  | awaiting PR | 30000000
| #REF! | 9 | Rain Curtain For Paon |  | 2026-03-13 | 100000000 | 2026-03-09 | 2026-04-09 | 25 | internal | 2026-04-30 | 2026-04-30 | 2026-05-21 | 67
|  | 10 | Digital Curtain For Chapel |  | awaiting PR | 200000000 | 2026-03-09 | 2026-04-09 | 25 | internal | 2026-04-30 | 2026-04-30 | 2026-05-21 | 67
|  | 11 | AEI - HENRY'S | FITOUT & FURNITURE FFNE, OSNE & IT |  | 1500000000 | 2026-03-09 | 2026-04-09 | 25 | by ID consultant | 2026-04-30 | 2026-04-30 | 2026-05-21 | 67
IKG | #REF! |  | SAND STORAGE | cancelled by GM | 2025-12-09 | [6 empty] | cancelled by GM
|  | 12 | AEI - EAGLE ROOM | FITOUT & IT, MEP |  | 760000000 | 2026-04-06 | 2026-05-07 | 53 | internal | 2026-05-28
ABD |  | 13 | AEI - BALLROOM & MEETING RM (2) | LIMITED TO FIT OUT + IT + Videotron for Ballroom |  | 3860000000 | 2026-03-02 | 2026-04-02 | 18 | internal | 2026-04-23
|  | 14 | REDRAW BUILDING | by ALTIRA |  |  | 2026-01-20 | 2026-02-20 | -23 | To complete the redrawing of all general plans, elevations, sections, and necessary blow-up details | 2026-03-13
| #REF! | 15 | Buffet Island / Cluster Table |  | awaiting PR - Q3 | 45000000
| #REF! | 16 | Replacement Wooden Sauna & Machine |  | 2026-03-17 | 106000000 | [5 empty] | 2026-03-17
| #REF! | 17 | Repair Wall Entrance Hotel Side - Sumatera |  | awaiting PR - Q3 | 99500000
| #REF! | 18 | Restaurant Taruma Chair | replacement of broken chair, no changes on existing model - to proceed under ops/ unit |  | 57320618
ASM |  | 19 | AEI - MUR 18'TH : Q1 & Q1A | INTERIOR & FURNITURE exclude OSNE |  | 1287300000 | 2025-10-15 | 2025-12-01 |  | Redesign by LOKA |  |  | Completed |  | 1080400000 | 2025-12-18 | 2026-03-14 | 2026-03-16 | -2 | 100%
|  | 20 | 2025 : Room Renovation 8+3 units by MyDesign |  |  | 5350000000 |  | 2025-12-20 |  |  |  | 2025-02-07 | 2025-02-21 | temination on 35-40 % progress | 1311088769 | 2025-04-28 | 2025-08-18 |  |  | aborted project
|  | 21 | Room Dining Chair |  | awaiting PR | 199950000
AME |  | 22 | AEI - NEW GYM |  |  | 720000000 | 2025-12-01 | 2026-01-01 |  | TENDER DRAWING DONE 16 Feb 2026 |  | 2026-02-20 | 2026-03-13 | -2
|  | 23 | AEI - PEONY |  |  | 1390000000 | 2026-02-02 | 2026-03-05 | -10 | internal
|  | 24 | AEI - RIAS |  |  | 725000000 | 2026-04-01 | 2026-05-02 |  | LOKA
|  | 25 | 2025 : AME wood parquet | continue from 2025, REPLACE THE WOODEN PARQUET RESTAURANT AREA |  | 689750000 | [9 empty] | 2026-04-12 | 2026-05-12 |  | 58 | start 12 April
|  | 26 | 2025 : Wall lamp replacement at Guest Corridor | Replace the corridor wall lamp with the new design | 2025-10-24 |  | 2025-07-23 | 2025-11-26 |  | TENDER PROCESS |  | 2026-02-10 | 2026-03-11 | -4 | 144750000
|  | 27 | 2025 : Replace Dimmer lighting - Brightness at Lotus 1,2,3 | to liaise with Dharmawan Lighting to provide clear input on existing condition | 2025-11-19
|  | 28 | Glass window film 3M - at ballroom foyer + pool cafe + restaurant area (teppan, private, etc) |  | awaiting PR - Q3 | 292000000
|  | 29 | Wallpaper / wall painting alamanda foyer + landing area 9th floor |  | awaiting PR - Q4 | 50000000
|  | 30 | Sofa VIP |  | awaiting PR - Q4 | 60000000
|  | 31 | soundproof system Ballroom partition | gasket & accoustic system |  | 360000000 | [6 empty] | 2026-03-18 | APS | ONGOING
APL |  | 32 | AEI - THE LOUNGE (Legacy Lounge) |  |  | 880000000 | 2026-03-02 | 2026-04-02 | 18 | internal | 2026-04-23
|  | 33 | 2025 : PPR Pipe Replacement |  |  | 1455235717 | [6 empty] | 2025-11-20 |  | 1325902770 | 2025-11-28 | 2025-03-31 |  |  | Defect list
|  | 34 | 2025 : Replace ceiling corridor | relate with PPR. Timeline = feb 2026 (after replacement work completed) | awaiting PR | 264000000
|  | 35 | Facade Repair & Painting | to split between repair & aesthetic | awaiting PR - Q1 | 700000000
|  | 36 | 2025 : CORRIDOR CARPET | 12 level : 5th-18th awaiting ceilling work completion by 30 April | 2025-11-13 | 1101909160 |  | 2025-12-30 |  | ref num : 034.DAP.APL-CORRIDOR CARPET |  |  | 2026-02-24 |  | 758110439 |  | 2025-05-30
ALV |  | 37 | 2025 : WATERPROOFING Concrete Roof | Palm, Lobby Lounge, ebony, drop off | 2025-01-27 | Unbudgeted | [5 empty] | 2026-02-02 | 2026-02-23 | -20 | ONGOING
|  | 38 | AEI : MUR 6'th : deluxe & bussiness | INTERIOR & FURNITURE exclude OSNE |  |  | 2 Sept 2025 |  |  | BY LOKA |  |  | Completed |  | 1170828000 | 2025-12-03 | 2026-03-14 | 2026-03-14 | 0 | 100%
|  | 39 | LANDSCAPE : BOULEVARD |  |  |  | 2025-10-27 | 2026-01-05 |  | BY ALTIRA |  |  |  |  | 1165500000 | 2026-01-05 | 2026-02-09 | 2026-02-09 |  | 100% |  | 2026-02-09
|  | 40 | LANDSCAPE : GATE |  |  |  | 2025-11-13 | 2026-01-05 |  | BY ALTIRA | [5 empty] | 2026-01-11 | 2026-03-14 | 2026-02-16 | 26 | 76% (Awaiting signage)
|  | 41 | LANDSCAPE : CASCADE FOUNTAIN |  |  | 1500000000 | 2026-02-02 | 2026-03-05 | -10 | BY ALTIRA
|  | 42 | LANDSCAPE : LOBBY DROP OFF | SOFTSCAPE | [7 empty] | 2026-03-05 | 2026-03-27 | PENDING CONTRACT | 475884857 | 2026-04-06 | 2026-04-21 |  |  | 0%
|  | 43 | ENTRANCE SIGNAGE |  |  |  | 2026-02-02
|  |  | 2025 : MAHOGANY REPAIR ROOF FRAMES/ JASMINE GARDEN | unbudgeted & current status is on site investigation |  | 350000000
ACC |  | 44 | REPAIR SURFACE TENNIS COURT 5&6 | defect list rectification | [11 empty] | 2026-02-07 | 2026-03-17 | 2026-03-10 | 7 | 100% |  | 2026-03-17
|  | 45 | PATHWAY REPAIR | 1,5 meters width | 2025-07-31 |  | 2025-07-31 |  |  | Mock up approved 9 Sept |  | 2025-08-21 | 2025-08-29 |  | 375000000 | 5 Sept 2025 | 2025-12-07 |  | -98 | 30,33%
|  |  |  | introduce new vendor : ALTIRA | [7 empty] | 2026-03-02 |  | PENDING CONTRACT |  | 2026-03-02 |  |  |  | done 142 m2
|  | 46 | ACC TENNIS COURT BENCHES | [9 empty] | 2025-12-23 |  | 96000000 |  | 2025-03-14 | 2025-03-11 | 3 | 100% onsite |  | 2025-03-14
AMD |  | 47 | FR : FACADE REPAIR & REPAINTING | FIRST REIT REIMBURSEMENT |  | 630000000 | [6 empty] | 2026-03-10 |  | 630000000 | 2026-02-19 | 2026-05-30 |  |  | 26,2%
|  | 48 | Furniture for outdoor amicoo |  | awaiting PR - Q3 | 15000000
|  | 49 | Sofa banquet |  | awaiting PR - Q3 | 24000000
|  | 50 | Director chair for meeting room |  | awaiting PR - Q3 | 12000000
|  | 51 | Portable folded partition |  | awaiting PR - Q3 | 10000000
|  | 52 | Lazy susan | rotating glass piece on a dining table - to proceed under ops/ unit |  | 40000000
APK |  | 53 | ROOF WATERPROOFING | under 2025 capex & nott to proceed until June 2026 | awaiting PR & TBC | 202240000
Formulas:
BAST -1 = [ACTUAL COMPLETION]
BAST -1 = [END CONTRACT]
DESIGN APPROVAL (+1 month) = [START DESIGN DATE]+31
WORKING DRAWING (+3 weeks) = [DESIGN APPROVAL (+1 month)]+21
TENDER START = [WORKING DRAWING (+3 weeks)]
TENDER START = [RECEIVED DATE]
APS = SPK RELEASED (+3 weeks) = [TENDER START]+21
ACTUAL COMPLETION = [END CONTRACT]
COMMENCE DATE = [TENDER START]